Project Management Processes

1.Determine the Input, Process and Exit criteria for each of the project management processes

I. Project Initiation

Input	Process	Output
Interviews with customer and other key personnel /  / Strategic documentation /  / Customer literature /  / Lessons learned from previous projects	Interview Customer / Conduct Internal Research / Develop solution and requirements / Review Lessons learned / Review customer requirements / Define project roles / Assemble core project team / Develop High-level WBS / High-level risk Assessment / Develop Cost estimate / Develop high-level Project charter / Review the owners for approval	Opportunity Summary /  / Pre-Project Budget Worksheet /  / Opportunity Assessment Detail /  / Quality Assurance Template /  / High Level WBS /  / High Level Risk Assessment /  / Client Cost Benefit Analysis /  / Problem Identification /  / Proposal Checklist /  / Project Proposal Document /  / High Level Project Charter

II. Project Planning

Input	Process	Output
High Level Project Charter (with attachments) /  / High Level Risk Assessment /  / Requirements Document	Conduct a Project Team Detailed Planning Meeting and Work Session / Develop detailed WBS / Develop the responsibility matrix / Develop Communications plan / Risk assessment and management planning / Define Human Resource Skill Requirements / Schedule Preparation / Develop cost management plan / Measuring Quality / Project procurement plans / Obtain communication plan approval / Finalize Project Charter / Conduct Management Review with owner / Develop Baselines	Communications Plan / Communications Matrix / Issue Log / Action Item Log / Documentation Matrix / Status Reports / Organization Chart / Project Team Directory / Project Charter / Resource Request Form / Project WBS / Requirements Traceability matrix / Responsibility Matrix / Risk Management Guide / Project Notebook / Developing Task Worksheet / Project Schedule

III. Project Execution phase

Input	Process	Output
Project Team /  / Project WBS /  / Communication Plan /  / Risk Management Plan /  / Organization Chart /  / Responsibility Matrix /  / Project Notebook /  / Issues/Action Item Log /  / Status Reports /  / Project Schedule	Tracking / Status meeting / Change Management / Maintaining quality / Project Documentation / Executive Review Meeting Facilitation / Monitor and Control Project risk / Manage and Resolve HR Conflicts / Adjust Schedules / Troubled Project Process / Complete the Phase Sign-off / Conduct interim project review with owner	Current and updated project schedule / Change Management / Quality Management / Phase Sign-off

IV. Project Monitoring and Controlling phase

Input	Process	Output
Project Schedule / Project Notebook / Issues/Action Outcome Log	Check for Scope boundary / Check on Quality policy	Progress and status reports / plan Updates / Risk registers / Change Requests / Work products/deliverables

V. Project Closure Phase

Input	Process	Output
Completed, up-to-date project schedules /  / All project documentation /  / Quality Checklists / Phase Sign-offs, as appropriate	Administrative Closure / Survey the project participants / Conduct post-implementation phase / Develop Lessons Learned / Send Documentation to Repository / Hold Project Celebration	Cost Implementation Review /  / Performance Evaluations /  / Lessons Learned /  / Project Evaluation /  / Delivery of Final Documentation /  / Project Sign-Off /  / Customer Satisfaction Survey